## project_nicholas
MR | Health | Primary | Details | Start Date | End Date | % Complete | Working Days Remaining | Status | Assignee | Duration | Dependency | Modified | Modified By | Column15 | Column16
|  | Project Information | [9 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | General Information | [9 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Stony Brook Medicine.png | Agency Logo | <---- Insert Agency Logo to Left | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Name | Nicholas Center - Behavioral Indicators | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Address | 382 Main Street, Port Washington, NY, 11050 | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Manager | Jeremy | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Owner | The Nicholas Center | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Sponsor | Stony Brook University AHI Program | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Client | The Nicholas Center | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Scope | Please see project charter document | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Project Type | migration | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Status | [9 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Current Project Health | RED | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Last Week Health | RED | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | This Week Status | Currently this project is in the process of proposing an IRB proposal and scoping migration on these technologies within the QoL application. It is in red because it need funding. | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Date of Status Update | 12/02/24 | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Assets & Documentation | [9 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Client Brief | Please see project charter document | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Approved Estimate | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Phone Smartsheet | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Teams Site | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | [Additional Document] | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Finances | [9 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Total Project Budget | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Total Actuals | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Budget Remaining | TBD | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Configuration | Complete |  |  |  | Remaining |  |  |  |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Completion % | 0% |  |  |  | 100% |  |  |  |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Expected End Date | 02/25/26 4:59 PM | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Expected Duration | 143 Days | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Number of Tasks in Red | 0 | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
|  | Workdays Remaining | 323 Days | [8 empty] | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
TRUE | Green | Nicholas Center - Behavioral Indicators Project Plan |  | 2024-08-25 | 2024-08-25 | 0% | 323 | In Queue |  | 143d |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
TRUE | RED | External Dependencies: |  | 2024-09-18 | 2024-09-18 | 0% | 221 | In Queue |  | 0 |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Red | Funding |  | 2025-10-06 | 2024-12-02 | 0% | 221 | In Queue |  | 0 | 48 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Conversion Planning |  | 2025-10-07 | 2025-12-30 | 0% | 282 | In Queue |  | 61d |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Determine Conversion Strategy |  | 2025-10-07 | 2025-11-03 | 0% | 241 | In Queue |  | 20d | 48 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Schedule Equipment Installation Date |  | 2025-12-17 | 2025-12-30 | 0% | 282 | In Queue |  | 10d | 146FF | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Set Conversion Date |  | 2025-12-24 | 2025-12-30 | 0% | 282 | In Queue |  | 5d | 146FF | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Plan for Scheduling Reductions |  | 2025-12-03 | 2025-12-30 | 0% | 282 | In Queue |  | 20d | 146FF | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Have Practice provide weekly schedule with volumes |  | 2025-12-17 | 2025-12-30 | 0% | 282 | In Queue |  | 10d | 146FF | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Conversion |  | 2025-12-30 | 2025-12-30 | 0% | 282 | In Queue |  | 1d |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
TRUE | Blue | Go-Live |  | 2025-12-30 | 2025-12-30 | 0% | 282 | In Queue |  | 1d | 34, 55, 85, 95, 103 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Post Conversion Support |  | 2025-12-31 | 2026-02-03 | 0% | 307 | In Queue |  | 25d |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Week 1 Full support 1:1 for MD's |  | 2025-12-31 | 2026-01-06 | 0% | 287 | In Queue |  | 5d | 146 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Week 2-3 Shared support |  | 2026-01-07 | 2026-01-20 | 0% | 297 | In Queue |  | 10d | 148 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Week 4-5 on site support transition to off-site |  | 2026-01-21 | 2026-02-03 | 0% | 307 | In Queue |  | 10d | 149 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Post Conversion Agreement |  | 2026-02-04 | 2026-02-25 | 0% | 323 | In Queue |  | 16d |  | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Lessons Learned Meeting |  | 2026-02-04 | 2026-02-04 | 0% | 308 | In Queue |  | 1d | 147 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu
| Blue | Project Turnover |  | 2026-02-05 | 2026-02-25 | 0% | 323 | In Queue |  | 15d | 152 | 2024-12-02 09:33 | alicia.bonavita@stonybrookmedicine.edu